こんにちは。お疲れ様です。

こちら側はみんな揃っています。そちらは皆さんお揃いですか。

それでは、はじめましょう。

今日のアジェンダとしてはプロジェクトの進捗と問題があります。

まず、プロジェクトの進捗を報告します。

＊　コーディングについてはインプリメントとチームのレビューとSSEレビューを完了しました。そして、CTGレビューは進行中（しんこうちゅう）です。SSEというのシニアソフトウェアエンジニアです。CTGというのは共通（こうつう）技術（ぎじゅつ）グループです。締切日は金曜日です。

完了日は６月２９日の予定です。

＊　ユニットテストについては設計が進行中となっています。ユニットテストのスクリプトを調査することを完了させました。しかし、ユニットテストの仕様書と実行がまだ実施していません。

完了日は7月６日の予定です。

＊　結合試験（けつごうしけん）に関しては設計と仕様書（しようしょ）の作成が完了しました。結合試験のスクリプトを作ることがプロセス中です。そして、統合テストの実行（じっこう）がまだしません。

完了日は7月１２日の予定です。

＊　システムテストについてはシステムテストの設計と仕様書（しようしょ）の作成が完了しました。システムテストのスクリプトの作成は進行中です。しかし、システムテスト実施の方（ほう）はまだ開始（かいし）していません。

完了日は7月１７日の予定です。

次は今週の問題です。

＊　一番目（いちばんめ）の問題はお客様から、ソフト詳細設計（しょうさいせっけい）のフィードバックがまだ来ていません。早く送っていただきます。

＊　二番目（にばんめ）の問題はAPIに関して一部（いちぶ）のパフォーマンスが低いことです。Z1とZ5のAPIです。原因はまだわかりません。教えていただきます。

こちらは以上です。

そちらは大丈夫ですか。

|  |
| --- |
| 1. Purpose of Meeting (0718) |
| Review project status.  Discussion about project issue.  Discussion on next SRS template, milestone |

|  |
| --- |
| 3. Discussion |
| 1. Project status.  |  |  |  | | --- | --- | --- | | **Task** | **Status** | **Complete date** | | CD | Completed | Jun 29, 2017 | | UT | Completed | July 06, 2017 | | IT | Completed | Jul 12, 2017 | | ST | * Make STD: Done * Make STS: Done * Execute test by manual: Done   + Found 19 bugs related to warning message.  +Un-test: 24 related to deploy/un-deploy.   * Create auto test script: Passed 250/434 test cases.   + Un-develop: 65 test scripts. Reason: Difficult or un-know execution method (24)   * Execution able: 250 test cases | Jul 20, 2017 |  1. Review result of last meeting.  |  |  |  | | --- | --- | --- | | **Issue** | **Action** | **Status** | | Monitor performance risk | Discuss with TSOL for performance risk. | Jul 18, 2017 | | Communicate with customer by Japanese | -Define organization.  -Prepare in Jul | In progress. |  1. Issue in this week.  |  |  |  |  |  | | --- | --- | --- | --- | --- | | **Issue** | **Redmine** | **Action** | **PiC** | **Deadline** | | Confirm about test environment:  -Chrome: V59  -Firefox: V47 | http://10.18.18.139/redmine/issues/120 | Notify to customer  ->Fukushima-san OK about that | ChinhHT | Jul 18, 2017 | | Confirm solution with performance risk. | http://10.18.18.139/redmine/issues/122 | Get confirmation  (Please refer redmine ticket)  => TSDV do not need monitor this risks | Fukushima-san | Jul 18, 2017 | | 24 un-tested cases |  | TDSL guide execution method | Fukushima-san | Jul 18, 2017 | | Confirm about behavior when user multi-click button | http://10.18.18.139/redmine/issues/121 | Notify to customer, get confirm  => Fukushima-san ok about TSDV’s suggestion | Fukushima-san | Jul 18, 2017 | | Scope of testing Workspace with multiple – changing status(like “killed”, “finished”, “failed”, “running” | http://10.18.18.139/redmine/issues/119 | Notify to customer, get confirm  => Oikawa-san has updated the guideline, TSDV will try to test these test cases. | Oikawa-san | Jul 18, 2017 |  1. Others  * Discuss on requirement of next task: Template, Milestone.   -TSDV will start testing (selenium and manual) from August.  -TSOL investigate about performance of Spark Streaming and may be changed to Apache Flink (some changes of GUI and workspace API may be made).  - August, Fukushima-san and Nakano-san will come to TSDV for discussing Grid DataLake product. |

こんにちは。お疲れ様です。

こちら側はみんな揃っています。そちらは皆さんお揃いですか。

それでは、はじめましょう。

今日のアジェンダとしてはプロジェクトの進捗と問題とSRSテンプレートがあります。

まず、プロジェクトの進捗を報告します。

＊　コーディングとユニットテストと結合試験については完了しました。

＊　システムテストについては設計と仕様書（しようしょ）が完了しました。

‐マニュアルで試験の実施した。結果については１９バグを見つかりました。” deploy/un-deploy“　機能に関して、２４テストケースはまだ実施できません。原因は“killed”, “finished”, “failed”, “running”というワークスペースの状態が作ってできませんでした。

‐Seleniumスクリプトについて、434テストケースの中に250テストケースが正し実施しました。65テストケースはまだインプリメントしませんでした。難しくて、実施が分かりませんから。

完了日は7月20日の予定です。

次は今週の問題です。それぞれの問題、意見を教えていただきます。

＊　一番目（いちばんめ）の問題はテストの環境（かんきょう）です。クロムのバジョンは59です。ファイアフォックスのバジョンは47です。これはだいじょうぶですか。教えていただきます。

＊　二番目（にばんめ）の問題はパフォーマンスのリスクです。将来、どうやってパフォーマンスを管理ですか。教えていただきます。

＊

こちらは以上です。

そちらは大丈夫ですか。

0725

|  |
| --- |
| 1. Purpose of Meeting |
| Review project status.  Discussion about project issue.  Discussion on next SRS template, milestone |

|  |
| --- |
| 3. Discussion |
| 1. Project status.  |  |  |  | | --- | --- | --- | | **Task** | **Status** | **Complete date** | | CD | Completed | Jun 29, 2017 | | UT | Completed | July 06, 2017 | | IT | Completed | Jul 12, 2017 | | ST | Completed with some limitation:  + Selenium: 348/435 test cases.  + 2 IT test case, 4 ST test cases couldn’t execute. (NA)  + Haven’t execute the test in IE11.  Results:  -TDSL understood and confirm status. | Jul 21, 2017 |  1. Review result of last week.  |  |  |  | | --- | --- | --- | | **Issue** | **Action** | **Results** | | Risk with quality of workspace module: TSDV didn’t execute UT for this module but we can detect 2 bugs in this module in IT phase | Notified to TDSL the bug | TDSL understood the risk and TDSL executed the test to warranty the quality of this module. | | Risk with long holidays of TDSL in Aug: We plan to execute test with IE11 in Aug. TSDV managers request us update milestone of this activities for better support plan from TSDV. | Discuss with TDSL about testing milestone for IE11. | Deadline for IE11 test in TSDV is end of Aug. |  1. Issue in this week.  |  |  |  |  | | --- | --- | --- | --- | | **Issue** | **Action** | **PiC** | **Deadline** | | Discussion on next plan: | Discussion on with TDSL:  -Target until end of Sep.  -Deliverable product.  Results:  -Deliverable is GDAC.  -In Sep, both side will focus on new Data Lake SRS. | ChinhHT | 25 Jul 2017 | | Discussion on SRS template | Show SRS template to customer and discussion on difficulty of template  Results:  -Current template may not suitable with characteristic of Data Lake: Requirement will update frequently based on latest technical.  🡪 F2F discussion in business trip of TDSL at the end of Aug | ChinhHT | 25 Jul 2017 | |  |  |  |  |  1. Others  * Business trip plan of TDSL to TSDV: 22/Aug – 25/Aug * TDSL feedback after 1st phase (Apr 🡪 Jun) |

こんにちは。お疲れ様です。

こちら側はみんな揃っています。そちらは皆さんお揃いですか。

それでは、はじめましょう。

今日のアジェンダとしてはプロジェクトの進捗と問題があります。

まず、プロジェクトの進捗を報告します。

＊　コーディングについてはインプリメントとチームのレビューとSSEレビューを完了しました。そして、CTGレビューは進行中（しんこうちゅう）です。SSEというのシニアソフトウェアエンジニアです。CTGというのは共通（こうつう）技術（ぎじゅつ）グループです。締切日は金曜日です。

完了日は６月２９日の予定です。

＊　ユニットテストについては設計が進行中となっています。ユニットテストのスクリプトを調査することを完了させました。しかし、ユニットテストの仕様書と実行がまだ実施していません。

完了日は7月６日の予定です。

＊　結合試験（けつごうしけん）に関しては設計と仕様書（しようしょ）の作成が完了しました。結合試験のスクリプトを作ることがプロセス中です。そして、統合テストの実行（じっこう）がまだしません。

完了日は7月１２日の予定です。

＊　システムテストについてはシステムテストの設計と仕様書（しようしょ）の作成が完了しました。システムテストのスクリプトの作成は進行中です。しかし、システムテスト実施の方（ほう）はまだ開始（かいし）していません。

完了日は7月１７日の予定です。

次は今週の問題です。

＊　一番目（いちばんめ）の問題はお客様から、ソフト詳細設計（しょうさいせっけい）のフィードバックがまだ来ていません。早く送っていただきます。

＊　二番目（にばんめ）の問題はAPIに関して一部（いちぶ）のパフォーマンスが低いことです。Z1とZ5のAPIです。原因はまだわかりません。教えていただきます。

こちらは以上です。

そちらは大丈夫ですか。